## Slide 1: Intelligent Ethernet-to-Fiber Converter
Redundant optical paths with real-time SFP health monitoring
ECE 4015 Capstone, Fall 2026
Notes: Project scope summary. Target demonstration date: December 8, 2026.

## Slide 2: Project target and scope
A media converter that monitors optical health and transfers Ethernet traffic before a fiber path fails.
TARGET
Maintain a 1 Gb/s Ethernet connection between two laptops across redundant 1000BASE-SX fiber paths.
PROTOTYPE
Two identical converter boards. Each board combines an STM32N6, LAN96455F switch, two SFP modules, and copper Ethernet ports.
SUCCESS CRITERIA
Report SFP diagnostics, identify a degrading primary path, coordinate both boards, and move traffic to the backup path.
Notes: Scope reflects the current two-board architecture. The first prototype targets 1 Gb/s multimode fiber and a controlled break-before-make failover demonstration.

## Slide 3
Market research and problem–solution
MARKET EVIDENCE
CURRENT GAP
OUR SOLUTION
Redundant SFP infrastructure already exists.
Cisco documents dual-SFP uplinks for redundant connectivity to the network core. Perle also sells dual-SFP media converters with primary/backup fiber failover. This means some deployments can leverage ports and fiber paths that are already provisioned rather than adding a new backup link solely for our feature.
Redundancy is usually reactive.
Commercial redundancy products switch after link failure; Perle specifies failover when the primary link fails. Basic industrial converters from Advantech expose Link Fault Pass-through but only one fiber port. Meanwhile, SFP DOM/DDM already exposes Rx/Tx optical power, temperature, voltage and laser-bias data.
Turn telemetry into proactive failover.
Our controller continuously evaluates SFP health, applies thresholds/hysteresis, and coordinates both converter boards to move 1 Gb/s traffic to the standby path before a hard loss-of-signal event. Value proposition: use existing redundancy more intelligently, with little or no added optical-infrastructure cost where a backup SFP path is already deployed.
DIFFERENTIATION
Existing: “detect failure → switch” → Proposed: “detect degradation → switch before failure”
Research basis: Cisco dual-SFP uplink guidance + SFP DOM/DDM; Perle dual-fiber redundancy; Advantech Link Fault Pass-through.

## Slide 4: System architecture
Data path
Laptop traffic passes through the LAN96455F hardware switch. The active SFP pair carries user data and in-band management frames.
Control path
Each STM32 reads local SFP diagnostics. Board A arbitrates the active path while Board B applies the coordinated port state.
Laptop A
BOARD A
LAN96455F
Ethernet switch
STM32N6
control
SFP0 / SFP1
Laptop B
BOARD B
LAN96455F
Ethernet switch
STM32N6
control
SFP0 / SFP1
PRIMARY AND BACKUP 1000BASE-SX
Full duplex fiber pairs
Notes: The diagram is intentionally simplified. Ethernet data and STM32-to-STM32 management frames share whichever optical path is active. Sources: https://www.microchip.com/en-us/product/lan96455 and https://www.st.com/en/microcontrollers-microprocessors/stm32n6-series.html

## Slide 5: System architecture
Notes: The diagram is intentionally simplified. Ethernet data and STM32-to-STM32 management frames share whichever optical path is active. Sources: https://www.microchip.com/en-us/product/lan96455 and https://www.st.com/en/microcontrollers-microprocessors/stm32n6-series.html

## Slide 6: System architecture
Notes: The diagram is intentionally simplified. Ethernet data and STM32-to-STM32 management frames share whichever optical path is active. Sources: https://www.microchip.com/en-us/product/lan96455 and https://www.st.com/en/microcontrollers-microprocessors/stm32n6-series.html

## Slide 7: Implementation plan
Critical path
1 Freeze interfaces, straps, power rails, clocks, and component selections
2 Complete schematic review and controlled-impedance PCB layout
3 Bring up power, STM32 boot flash, switch management, copper ports, and each SFP path
4 Add telemetry thresholds, coordinated failover, and repeatable fault injection
HARDWARE
STM32N6 boot and debug
LAN96455F unmanaged boot
RGMII and 1000BASE-X routing
SFP power and diagnostics
FIRMWARE AND VALIDATION
SPI switch control and SFP I²C reads
Health scoring and hysteresis
Cross-board arbitration
Traffic and failover measurements
Notes: The highest schedule risks are first-pass board bring-up, LAN96455 configuration, and coordinated failover behavior. Keep manual port switching available as an early demonstration fallback.

## Slide 8: Working timeline to the December 8 expo
SEP 8–30
OCT 1–NOV 15
NOV 16–DEC 8
PCB and bring-up
Fabrication, assembly, rail checks, STM32 boot, switch access, and individual links.
Architecture and schematic
Freeze parts, interfaces, boot straps, power tree, schematic pages, and layout.
Integration and demo
Telemetry thresholds, coordinated failover, traffic testing, enclosure, and presentation rehearsal.
Notes: Working schedule prepared September 8, 2026. The December 8 expo date comes from the project requirement. Intermediate dates are planning assumptions and should be updated after fabrication lead time is confirmed.